## Summary
Capacity Development Working Group - Action Plan
|  |  |  | Working Plan | Jun | Jul | Ago | Set | Oct | Nov | Dec | [6 empty] | Updated on | 10.19.2022
| 1 | Capacity Building Working Group | 1 | ToR | bar: Jun to Jul
|  |  | 2 | Regular Meetings | [8 empty] | Modalities: |  | Definition | bar: Jun to Dec
|  |  | 3 | Regular Updates in Training Activities | [8 empty] | CCCM Induction Training |  | 2 days training on CCCM Core Concepts and activities | bar: Jun to Dec
|  |  | 4 | Action Plan | [8 empty] | CCCM On-the Job Training |  | 1 day training followed by field mentoring visits and sessions for introduction of tools/SOPs and specific topics | bar: Jun to Ago
|  |  | 5 | Training Traking Tool | bar: Jun; Ago
|  |  | 6 | Learning Needs Assessments | [8 empty] | CCCM ToT |  | 5 days - on Training Methodology, CCCM Tools and Sessions | bar: Jun; Ago
|  |  | 7 | Contextualization of Training Package | [8 empty] | MSCM |  | 12 independent modules | bar: Jun to Ago
|  |  | 8 | Translation of Training Package | [8 empty] | GBV/PSEA on Sites |  | Joint training with Protection Cluster | bar: Jun to Oct
| 2 | Pool of Trainers | 9 | CCCM Induction Training | [8 empty] | Community Coordination |  | Training on Community Engagement, Community-Led Projects | bar: Jun to Dec
|  |  | 10 | Advocacy on complementary trainings (PSEA/GBV) | [8 empty] | Minimum Standards |  | 1h30 sessions on specific topics of the Minimum Standards on Site Management | bar: Jun; Ago to Set
|  |  | 11 | Mentoring of Training Activities | bar: Jun; Ago to Dec
|  |  | 12 | CCCM ToT | bar: Jun; Oct to Nov
| 3 | Training on Job | 13 | Definition of basic Tools | bar: Jun; Ago to Oct
|  |  | 14 | SoPs on Core Procedures | bar: Jun; Ago to Oct
|  |  | 15 | Implementation | bar: Jun; Ago to Dec
| Trainings Planned |  |  | Duration | Mai | Jun | Jul | Ago | Sep | Oct | Nov | Dez | 2 days/Induction | 1 day training + Monitored Visit + Sessions on Specific Topics/On-the-Job | 2 weeks | PSEA | GBV | Community | CCCM ToT
|  |  |  | Oblasts | [8 empty] | (8-12 sessions) |  | Optional Modules 1h30 (1-12 modules) | CCCM | CCCM | Coordination | Oct/Nov
|  |  | 0 | Regional |  | 1 | 1 |  | 1 | 1 | 2 | 2 |  |  | RedR UK/IOM
|  |  | 0 | National | [8 empty] | CCCM Cluster |  |  | PSEA WG | GBV WG | bar: Jul; Nov
|  |  | 1 | Zakarpatska | [8 empty] | IOM | UNHCR | bar: Jul to Ago
|  |  | 2 | Lvivska | [8 empty] | IOM/NRC | NRC |  |  |  |  | CCM Cluster | bar: Ago; Oct
|  |  | 3 | Chernivetska | [8 empty] | IOM | UNHCR | bar: Mai
|  |  | 4 | Ternopilska | [8 empty] | NRC | bar: Nov
|  |  | 5 | Ivano-Frankivska | [8 empty] | IOM | UNHCR | bar: Sep
|  |  | 6 | Vinnytska | [8 empty] | IOM/ACTED | bar: Mai; Sep
|  |  | 7 | Kirovohradska | [8 empty] | ACTED | bar: Mai
|  |  | 8 | Dinipropetrovska | Mai: 1; Sep: 2; Oct: 1 | IOM/ACTED | UNHCR |  |  |  |  | CCM Cluster
|  |  | 9 | Zaporizka | [9 empty] | UNHCR
|  |  | 10 | Volynska
|  |  | 11 | Rivneska | [9 empty] | UNHCR
|  |  | 12 | Kyivska
|  |  | 13 | Chernihiv Oblast
|  |  | 14 | Odeska
|  |  | 15 | Poltavska | [8 empty] | IOM | bar: Sep
|  |  | 16 | Zhytomyrska
|  |  | 17 | Kharkivska
|  |  | 18 | Khmelnytskyi
|  |  | 19 | Zhytomyr
[5 empty] | 4 | 1 | 3 | 2 | 6 | 3 | 4 | 2
|  | Indicators Reached |  |  | Jun | Jul | Ago | Sep | Oct | Nov | Dez | Total |  | Trainings Registration - Ukraine:
|  |  |  | # People trainned | Jun: 27; Jul: 58; Ago: 65; Sep: 92 | 242 |  | https://forms.office.com/r/ExmQbVu9w8
|  |  |  | # Capacity Building Activities | Jun: 4; Jul: 2; Ago: 3; Sep: 4 | 13
| People trained on CCCM in Ukraine - Aug.26 |  |  | Ukraine | CCCM Cluster | ACTED | IOM | UNHCR | NRC | RedR UK | People Trained | Induction Training | On-the-Job Training | MSCM
Cherkasy Oblast
Chernihiv Oblast
|  |  |  | Chernivtsi Oblast | Jun: 2; Jul: 7; Nov: 47; Dez: 9 | 9 |  | 47
|  |  |  | Dnipropetrovsk Oblast | Jun: 8; Jul: 27; Ago: 22; Dez: 57 | 57
|  |  |  | Donetsk Oblast | [9 empty] | 1 | bar: Nov
|  |  |  | Ivano-Frankivsk Oblast | Ago: 27; Nov: 1; Dez: 27 | 27 |  | 1
|  |  |  | Kharkiv Oblast | Nov: 2 |  |  | 2
Kherson Oblast
|  |  |  | Khmelnytskyi Oblast | [7 empty] | 6 |  | 1
|  |  |  | Kyiv Oblast | Jun: 7; Dez: 7 | 7
|  |  |  | Kirovohrad Oblast | Jun: 1; Jul: 6; Nov: 47; Dez: 7 | 1 |  | 47
Luhansk Oblast
|  |  |  | Lviv Oblast | Jun: 2; Oct: 5; Nov: 50; Dez: 7 | 2 | 5 | 50
Mykolaiv Oblast
|  |  |  | Odesa Oblast | Jun: 2; Nov: 31; Dez: 2 | 2 |  | 31
|  |  |  | Poltava Oblast | Ago: 22; Nov: 2; Dez: 22 | 22 |  | 2
|  |  |  | Rivne Oblast | [9 empty] | 1 | bar: Nov
Sumy Oblast
|  |  |  | Ternopil Oblast | Oct: 4; Dez: 4 |  | 4
|  |  |  | Vinnytsia Oblast | Jun: 2; Jul: 8; Ago: 26; Dez: 36 | 36
Volyn Oblast
|  |  |  | Zakarpattia Oblast | Jun: 4; Ago: 30; Sep: 30; Dez: 64 | 34 | 30
|  |  |  | Zaporizhzhia Oblast | [9 empty] | 1 | bar: Nov
|  |  |  | Zhytomyr Oblast | [9 empty] | 1 | bar: Nov
|  |  |  | Total | 28 | 48 | 127 | 30 | 9 | 184 | 242 | 203 | 39 | 185
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.

## 4W
| Organization | Oblast | Type of Training | Target Partcipants | # | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dez
# |  |  | (IT_OTJ_MSCM_ToT) |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | ACTED |  | IT | Staff | 10-15 | bar: May W3
2 | ACTED |  | IT | Staff | 10-15 | bar: May W4
3 | ACTED |  | IT | Staff | 10-15 | bar: Jun W1
4 | ACTED |  | IT | Staff | 10-15 | bar: Jun W2
5 | ACTED |  | IT | Staff | 10-15 | bar: Jun W3
6 | RedR UK |  | IT | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 10-15 | bar: Jun W3 to Jun W4
7 | CCCM Cluster | National | IT | National Government, CCCM Partners | 25-30 | bar: Jul W1
8 | RedR UK | Regional | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Jul W2 to Jul W3
9 | IOM | Zakarpatska | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Jul W4
10 | UNHCR | Zakarpatska | OTJ | NGOs Patners | 25-30 | bar: Aug W2
11 | NRC | Lviv | OTJ | Staff | 25-30
12 | IOM | Vinnytsia | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Aug W3
13 | IOM | Dnipro | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Sep W1
14 | ACTED | Dnipro | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Sep W2
15 | IOM | Poltava | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Sep W2
16 | IOM | Ivano-Frankvisk | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Sep W3
17 | UNHCR | Kirovograd | OTJ | NGOs Patners | 25-30 | bar: Sep W4
18 | ACTED | Dnipro | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 20-25 | bar: Oct W2
19 | NRC | Lviv | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Oct W4
20 | NRC | Ternopil | IT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Nov W4
23 | RedR UK | National | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Oct W4 to Nov W1
21 | CCCM Cluster | Lviv | ToT | National Government, CCCM Partners | 25-30 | bar: Nov W2
22 | CCCM Cluster | Dnipro | ToT | National Government, CCCM Partners | 25-30 | bar: Nov W3
23.9644 | IOM |  | ToT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Nov W4
24.9615 | IOM |  | ToT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Dez W1
25.9585 | IOM |  | ToT | Oblast, Raion, Hromada Governments, Staff, Site Managers | 25-30 | bar: Dez W2
26.9555 | RedR UK | National | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Nov W4
27.9526 | RedR UK | National | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Dez W1
28.9496 | RedR UK | National | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Dez W2
29.9466 | RedR UK | National | MSCM | National, Oblast, Raion, Hromada Government, Humanitarian workers, NGOs | 20-25 | bar: Dez W3

## Indicators_Trainings
|  | Apr | Mai | Jun | Jul | Ago | Sep | Oct | Nov | Dez | Total
| # People trainned | Mai: 35; Jul: 58; Ago: 56; Sep: 108 | 257
| # Capacity Building Activities | Mai: 3; Jun: 2; Jul: 2; Ago: 2; Sep: 5 | 14
| Duration | Apr | Mai | Jun | Jul | Ago | Sep | Oct | Nov | Dez | 2 days | 1 day
| Oblasts | [9 empty] | (8-12 sessions) | (2-4 sessions)
0 | National | [9 empty] | CCCM Cluster | bar: Jul
1 | Zakarpatska | [9 empty] | IOM | UNHCR | bar: Jul to Ago
2 | Lvivska | [9 empty] | IOM/NRC
3 | Chernivetska | [9 empty] | IOM/ACTED | UNHCR | bar: Mai
4 | Ternopilska | [9 empty] | NRC
5 | Ivano-Frankivska | [9 empty] | IOM | UNHCR | bar: Sep
6 | Vinnytska | [9 empty] | IOM/ACTED | bar: Mai
7 | Kirovohradska | [9 empty] | ACTED | bar: Sep
8 | Dinipropetrovska | Sep: 2 | IOM/ACTED | UNHCR
9 | Zaporizka | [10 empty] | UNHCR
10 | Volynska
11 | Rivneska | [10 empty] | UNHCR
12 | Kyivska | [9 empty] | IOM
13 | Odeska | [9 empty] | ACTED | bar: Mai
14 | Poltavska | [9 empty] | IOM | bar: Sep
15 | Zhytomyrska
16 | Kharkivska
17 | Khmelnytskyi
18 | Zhytomyr

## Indicators_People Trained
last update: 12.11.2022
People trained by Oblast
Ukraine | CCCM Cluster |  | ACTED |  | IOM |  | UNHCR |  | NRC |  | RedR UK | People Trained | Induction Training | On-the-Job Training (OtJ) | CCCM ToT | Minimum Standards in Site Management
| Induction | ToT | Induction | OtJ | Induction | ToT | Induction | OtJ | Induction | OtJ
Cherkasy Oblast
Chernihiv Oblast
Chernivtsi Oblast | 2 | 3 | 7 |  |  |  |  | 2 |  |  | 47 | 14 | 9 |  | 3 | 47
Dnipropetrovsk Oblast | 8 | 10 | 83 |  | 22 |  |  | 20 |  |  |  | 143 | 113 |  | 10
Donetsk Oblast | [10 empty] | 1 |  |  |  |  | 1
Ivano-Frankivsk Oblast |  | 1 |  |  | 27 | 27 |  | 8 |  |  | 1 | 63 | 27 | 8 | 28 | 1
Kharkiv Oblast |  | 1 | [8 empty] | 2 | 1 |  |  | 1 | 2
Kherson Oblast
Khmelnytskyi Oblast | [15 empty] | 1
Kyiv Oblast | 7 | 2 | [9 empty] | 9 | 7 |  | 2
Kirovohrad Oblast | 1 | 3 | 66 |  |  |  |  | 17 |  |  | 47 | 87 | 67 | 17 | 3 | 47
Luhansk Oblast
Lviv Oblast | 2 | 10 | [5 empty] | 4 | 4 | 5 | 50 | 25 | 6 | 9 | 10 | 50
Mykolaiv Oblast | [7 empty] | 6 |  |  |  | 6 |  | 6
Odesa Oblast | 2 | 4 | [5 empty] | 25 |  |  | 31 | 31 | 2 | 25 | 4 | 31
Poltava Oblast |  | 2 |  |  | 22 | [5 empty] | 2 | 24 | 22 |  | 2 | 2
Rivne Oblast |  | 3 | [8 empty] | 1 | 3 |  |  | 3 | 1
Sumy Oblast
Ternopil Oblast | [9 empty] | 4 |  | 4 |  | 4
Vinnytsia Oblast | 2 | 2 | 8 |  | 26 | [6 empty] | 38 | 36 |  | 2
Volyn Oblast
Zakarpattia Oblast | 4 |  |  |  | 30 |  |  | 10 |  |  |  | 44 | 34 | 10
Zaporizhzhia Oblast | [10 empty] | 1 |  |  |  |  | 1
Zhytomyr Oblast | [10 empty] | 1 |  |  |  |  | 1
Total | 28 | 41 | 164 |  | 127 | 27 |  | 92 | 4 | 9 | 184 | 492 | 323 | 79 | 68 | 185
[14 empty] | other |  | 83
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel.
Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Training Registration Form
ID | Start time | Completion time | Email | Name | Name | Email2 | Trainer(s) Name(s) | Trainer(s) Email(s) | Start date of the event | End date of the event | Duration of the event (in days) | Total number of participants | Total number of female participants | Total number of male participants | Total number of gender not declared participants | Was the training conducted remotely? | Oblast/Location of Event | City/Location of Event | Homadas covered by the event | Languages of the Event | Training Type | Primary Geographical Focus of Event | How will participants apply their learning? | Displacement Setting | Displacement Enviroment | Level of Event | Comments | Have the participants list been shared with ukrkicccm@unhcr.org | Have the participants list been shared with ukrkicccm@unhcr.org2 | Oblast/Location of Event2 | Raions/Districts covered by the event | Raions/Districts covered by the event2 | Cherkasy Oblast (Raions) | Chernihiv Oblast (Raions) | Chernivtsi Oblast (Raions) | Dnipropetrovsk Oblast (Raions) | Donetsk Oblast (Raions) | Ivano-Frankivsk Oblast (Raions) | Kharkiv Oblast | Kherson Oblast (Raions) | Khmelnytskyi Oblast | Khmelnytskyi Oblast (Raions) | Kirovohrad Oblast (Raions) | Kyiv Oblast | Luhansk Oblast | Lviv Oblast (Raions) | Mykolaiv Oblast (Raions) | Odesa Oblast (Raion) | Poltava Oblast (raions) | Rivne Oblast (Raions) | Sumy Oblast (Raions) | Ternopil Oblast (Raions) | Vinnytsia Oblast (Raions) | Volyn Oblast (raions) | Zakarpattia Oblast | Zaporizhzhia Oblast (raions) | Zhytomyr Oblast (Raions) | Organization | Participants Organizations | Type of participants'' organizations | Oblast/Location of Event3 | Oblast/Location of Event4 | Oblast/Location of Event5 | Oblast/Location of Event6
1 | 2022-08-22 14:14 | 2022-08-22 14:22 | anonymous | [5 empty] | 2022-07-26 | 2022-07-27 | 2 | 30 | 18 | 12 | 0 | No | Zakarpattia | Uzhgorod | Uzhgorod | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Core CCCM modules were covered with sources from the global package and national cccm cluster. Training was conducted with Ukraine translator for entire duration. | Yes |  | Zakarpattia Oblast | Uzhgorod | [23 empty] | Uzhgorod |  |  | ACTED |  | Local Government - City Council;Non-Governmental Organization (NGO);UN Agency;
2 | 2022-08-25 10:15 | 2022-08-25 10:34 | anonymous | [5 empty] | 2022-06-06 | 2022-06-06 | 2 | 8 | 8 | 8 | 0 | No | Vinnytsia | Vinnytsia | Vinnytsia | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Training for ACTED CCCM staff | Yes |  | Vinnytsia Oblast | Vinnytsia | [21 empty] | Vinnytsia |  |  |  |  | ACTED |  | Non-Governmental Organization (NGO);
3 | 2022-08-25 10:34 | 2022-08-25 10:36 | anonymous | [5 empty] | 2022-06-13 | 2022-06-13 | 2 | 7 | 3 | 4 | 0 | No | Chernivitsi | Chernivitsi | Chernivitsi | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Training for ACTED CCCM staff | Yes |  | Chernivtsi Oblast | Chernivitsi |  |  |  | Chernivitsi | [22 empty] | ACTED |  | Non-Governmental Organization (NGO);
4 | 2022-08-25 10:36 | 2022-08-25 10:39 | anonymous | [5 empty] | 2022-06-20 | 2022-06-20 | 2 | 6 | 3 | 3 | 0 | No | Kropyvnytskyi | Kropyvnytskyi | Kropyvnytskyi | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Peri-urban | Introductory | Training for CCCM ACTED staff | Yes |  | Kirovohrad Oblast; | Kropyvnytskyi | [11 empty] | Kropyvnytskyi | [14 empty] | ACTED |  | Non-Governmental Organization (NGO);
5 | 2022-08-25 10:39 | 2022-08-25 10:42 | anonymous | [5 empty] | 2022-06-27 | 2022-06-27 | 2 | 6 | 3 | 3 | 0 | No | Dnipro | Dnipro | Dnipro | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Training for CCCM ACTED staff | Yes |  | Dnipropetrovsk Oblast; | Dnipro |  |  |  |  | Dnipro | [21 empty] | ACTED |  | Non-Governmental Organization (NGO);
6 | 2022-08-30 10:38 | 2022-08-30 10:59 | anonymous | [5 empty] | 2022-08-29 | 2022-08-29 | 1 | 9 | 2 | 7 | 0 | Yes | Lvivska | Lviv | Stryiska,Morshynska,Novorozdilska,Truskavetska,Drohobychskaya,Lvivska,Sykhivska,Zhydachivskav,Khorostkivska,Kopychynetska,Terebovlianska,Ternopilska,Biletska,Zalishchytska | English;Ukrainian; | Site Management Training (Operational) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Peri-urban | Introductory | Introduction to CCCM, Humanitarian Principles, Coordination, Roles and Responsibilities | No |  | Lviviska Oblast; | Chortkivskyi,Ternopilskyi,Ternopilska,Stryiskyi,Truskavets,Drohobych,Galician,Lviv,Drohobytskyi | [14 empty] | Chortkivskyi,Stryiskyi,Truskavets,Drohobych,Galician,Lviv,Drohobytskyi | [5 empty] | Ternopilskyi,Ternopilska | [5 empty] | NRC |  | Non-Governmental Organization (NGO);
7 | 2022-09-02 22:40 | 2022-09-02 22:52 | anonymous | [5 empty] | 2022-08-29 | 2022-08-30 | 2 | 26 | 19 | 7 | 0 | No | Vinnytsia | Vinnytsia |  | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Core modules of CCCM focusing on collective center management | No |  | Vinnytsia Oblast | [22 empty] | Vinnytsia Raion; |  |  |  |  | UNHCR |  | Non-Governmental Organization (NGO);
8 | 2022-09-08 17:22 | 2022-09-08 18:22 | anonymous | [5 empty] | 2022-08-11 | 2022-08-11 | 1 | 30 | 15 | 15 | 0 | Yes | Zakarpattia | Uzhgorod | Lviv, Zakarpattia, Ivano-Frankvisk | English;Ukrainian; | Site Management Training (Operational) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Policy Development, Action Planning, etc. | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | N/A | Yes |  | Zakarpattia Oblast | [7 empty] | Ivano-Frankivsk Raion;Kolomyia Raion; | [19 empty] | IOM |  | Local Government - Oblast;Local Government - City Council;Local Government - Hromada;Non-Governmental Organization (NGO);UN Agency;
9 | 2022-09-13 12:08 | 2022-09-13 12:35 | anonymous | [5 empty] | 2022-07-01 | 2022-07-04 | 2 | 28 | 18 | 10 | 0 | Yes | National | Lviv | N/A | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | National - for people who will work in the capital or cover the whole country | Training of others who will then use theirs learning for direct benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | core CCCM modules generally adapted for Ukraine | Yes |  | National | n/a |  | Zvenyhorodka Raion; | [24 empty] | CCCM Cluster | Right to Protection Foundation; Rokada; TTA; UNHCR; NGO "April 10"; CrimeaSOS; ACTED; NEEKA; Ministry of Regional development; Ministry of Reintegration; IOM | National Government - Ministry;Non-Governmental Organization (NGO);International Non-Governmental Organization (INGO);UN Agency;
10 | 2022-10-03 06:11 | 2022-10-03 07:00 | anonymous | [5 empty] | 2022-09-20 | 2022-09-21 | 2 | 27 | 21 | 6 | 0 | No | Ivano-Frankvisk | Ivano-Frankvisk | N/A | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | core CCCM modules generally adapted for Ukraine | No |  | Ivano-Frankivsk Oblast | [7 empty] | Ivano-Frankivsk Raion;Kalush Raion;Kolomyia Raion;Kosiv Raion;Verkhovyna Raion;Nadvirna Raion; | [19 empty] | IOM | Executive committee of the Kalush City Council;Department of Social Protection of the Population of Kolomyia State Administration; Kolomyysʹkyy Tsentr Sotsialʹnoyi Reabilitatsiyi Ditey-Invalidiv; Department of Social Protection of the Population of the Kosiv District State Administration; Department of Social Protection and Provision of Social Services of the Solotvyn Settlement Council of the Ivano-Frankivsk District; Verkhovynsʹka Rayonna Derzhavna Administratsiya; Department of Community Integration, Internal Policy and Interaction with IDPs of the Ivano-Frankivsk City Council; Ivano-Frankivsk Regional Center of Social Services; Lanchynsʹka selyshchna rada of the Nadvirna district; Department of Social Policy of the Ivano-Frankivsk Regional Administration; Head Office of the National Service in the Ivano-Frankivsk region; Prosvita; Rokada; IOM | Local Government - Oblast;Local Government - City Council;Local Government - Hromada;Non-Governmental Organization (NGO);UN Agency;
11 | 2022-10-03 07:00 | 2022-10-03 07:14 | anonymous | [5 empty] | 2022-09-13 | 2022-09-14 | 2 | 22 | 17 | 5 | 0 | No | Poltava | Poltava | N/A | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | core CCCM modules generally adapted for Ukraine | Yes |  | Poltava Oblast | [18 empty] | Poltava Raion; | [8 empty] | IOM | Hotel Ukraine; Karlivka city council; Nekhvorosha village council; "Rehab center for Persons with Disability;" Novoselivka village council; Zelena Dubrava; College of Arts; Special school for the deaf; Mykilske special school; National Pedagogical University; Shyshaky Oblast Liceum; Shuger Company; Technical college #56; Mining and costruction college; Vepryk, Agrarian college; Rotary Club, R2P; Crimea SOS NGO; Light of Hope, IOM | Local Government - City Council;Non-Governmental Organization (NGO);UN Agency;
12 | 2022-10-03 07:15 | 2022-10-03 07:23 | anonymous | [5 empty] | 2022-09-06 | 2022-09-07 | 2 | 22 | 15 | 7 | 0 | No | Dnipro | Dnipro | N/A | English;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | core CCCM modules generally adapted for Ukraine | Yes |  | Dnipropetrovsk Oblast; | [5 empty] | Dnipro Raion;Kryvyi Rih Raion; | [21 empty] | IOM | ACTED, R2P, Rotary Dnipro, Rotary Kryvyi Rih, Proliska, Kryvyi Rih State Professional | Local Government - Oblast;Non-Governmental Organization (NGO);International Non-Governmental Organization (INGO);UN Agency;
13 | 2022-10-06 11:50 | 2022-10-06 13:56 | anonymous | [5 empty] | 2022-09-15 | 2022-09-16 | 2 | 21 | 15 | 6 | 0 | No | Dnipro | Dnipro | 5 | Ukrainian;English; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Training of others who will then use theirs learning for direct benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | Training consists of 8 sections based on the materials provided by the cluster СССМ | Yes |  | Dnipropetrovsk Oblast; | [5 empty] | Dnipro Raion; | [21 empty] | ACTED | ACTED, R2P, Proliska Dnepr, UNHCR | Local Government - City Council;Non-Governmental Organization (NGO);
14 | 2022-10-18 09:44 | 2022-10-18 10:19 | anonymous | [5 empty] | 2022-10-13 | 2022-10-14 | 2 | 18 | 12 | 6 | 0 | No | Dnipro | Dnipro | Dniprovska, Kryvorizka | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Urban | Introductory | CCCM Introduction training, material CCCM Cluster | Yes |  | Dnipropetrovsk Oblast; |  |  |  | Cherkasy Raion; | [23 empty] | ACTED | 0 | Local Government - City Council;
15 | 2022-10-25 10:41 | 2022-10-25 10:49 | anonymous | [5 empty] | 2022-10-20 | 2022-10-21 | 2 | 4 | 1 | 3 | 0 | No | Lvivska | Lvivska | Participants were NRC UDOC Project Coordinator and Team Leaders in charge of covering collective Centers across different Hromadas in Lviv and Ternopil Oblasts. | English; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Peri-urban | Intermediary | Introduction to CM, Roles & Responsibilities, Humanitarian Principles, Protection Mainstreaming, Coordination and Information Management, Service monitoring and Reporting, Community Participation and Accountability to Affected Population | No |  | Lviviska Oblast; |  |  | Zvenyhorodka Raion; | [24 empty] | NRC | Olena Komissarova, Yaroslav Matiash, Bohdan Kryzhanovskyi, Vitalii Zubyk | International Non-Governmental Organization (INGO);
16 | 2022-10-26 11:47 | 2022-10-26 16:27 | anonymous | [5 empty] | 2022-09-23 | 2022-09-23 | 1 | 17 | 10 | 7 | 0 | No | Kropyvnytskyi | Kropyvnytskyi | All oblast | English;Ukrainian; | Site Management Training (Operational) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Rural | Intermediary | "CCCM in action" workshop: Activities carried out by partners, community participation, legal framework, safety audit, CCCM deliverables, action planning | Yes |  | Kirovohrad Oblast; |  |  | Cherkasy Raion; | [24 empty] | UNHCR | ACTED, TTA | International Non-Governmental Organization (INGO);Non-Governmental Organization (NGO);
17 | 2022-10-26 16:27 | 2022-10-26 16:53 | anonymous | [5 empty] | 2022-10-21 | 2022-10-21 | 1 | 25 | 17 | 8 | 0 | No | Odessa | Odessa | Odesa, Mykolaiv, Kirovograd oblast | English;Ukrainian; | Site Management Training (Operational) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.) | Rural | Intermediary | Activities of the partners, CCCM deliverables, legal framework, code of conduct, safety audit, service mapping, area-based approach, action planning | Yes |  | Odesa Oblast; |  |  | Cherkasy Raion; | [24 empty] | UNHCR | TTA, ACTED | Non-Governmental Organization (NGO);International Non-Governmental Organization (INGO);
18 | 2022-11-08 12:16 | 2022-11-08 12:29 | anonymous | [5 empty] | 2022-11-03 | 2022-11-04 | 2 | 10 | 7 | 3 | 0 | No |  |  |  | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban; | Introductory | All materials received from the CCCМ cluster | Yes |  | Dnipropetrovsk Oblast; | [27 empty] | ACTED | Public organizations and representatives of shelters, IDPs | Non-Governmental Organization (NGO);Volunteers;Internal Displaced Persons; |  |  | Dnipropetrovsk Oblast - Dnipro Raion;
19 | 2022-11-14 08:33 | 2022-11-14 08:42 | anonymous | [5 empty] | 2022-11-11 | 2022-11-11 | 1 | 20 | 12 | 8 | 0 | No |  |  |  | English;Ukrainian; | Site Management Training (Operational) - CCCM in Action | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban;Peri-urban;Rural; | Intermediary | CCCM in Action Workshop | No |  | Dnipropetrovsk Oblast; | [27 empty] | ACTED | ACTED, R2P, UNHCR | International Non-Governmental Organization (INGO);Non-Governmental Organization (NGO);UN Agency; |  |  | Dnipropetrovsk Oblast - Dnipro Raion;Dnipropetrovsk Oblast - Kamianske Raion;Dnipropetrovsk Oblast - Kryvyi Rih Raion;Dnipropetrovsk Oblast - Nikopol Raion;Dnipropetrovsk Oblast - Novomoskovsk Raion;Dnipropetrovsk Oblast - Synelnykove Raion;Dnipropetrovsk Oblast - Pavlohrad Raion;Poltava Oblast - Poltava Raion;Poltava Oblast - Myrhorod Raion;Poltava Oblast - Lubny Raion;Poltava Oblast - Kremenchuk Raion;Zaporizhzhia Oblast - Zaporizhzhia Raion;Zaporizhzhia Oblast - Vasylivka Raion;Zaporizhzhia Oblast - Polohy Raion;Zaporizhzhia Oblast - Melitopol Raion;Zaporizhzhia Oblast - Berdiansk Raion;
20 | 2022-11-21 12:35 | 2022-11-21 12:56 | anonymous | [5 empty] | 2022-11-09 | 2022-11-10 | 2 | 14 | 11 | 3 | 0 | No |  |  |  | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Training of others who will then use theirs learning for direct benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban; | Introductory | Introductory training based on CCCM cluster materials | Yes |  | Dnipropetrovsk Oblast; | [27 empty] | ACTED | Educational institutions on the basis of which collective centers are located | Local Government - Hromada; |  |  | Dnipropetrovsk Oblast - Kryvyi Rih Raion;
21 | 2022-11-29 13:54 | 2022-11-29 18:57 | anonymous | [5 empty] | 2022-11-22 | 2022-11-23 | 2 | 9 | 5 | 4 | 0 | No |  |  |  | Ukrainian;Russian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Rural; | Introductory | Introduction to the course: Participants were introduced to the purpose of the course, clarified expectations from the training, discussed the rules of the training. Introduction to CCM: Participants got acquainted with what camp management is, considered different types of temporary accommodation and stages of the camp life cycle. An interactive discussion took place, during which it was considered that different IDPs need different protection and assistance. During the discussion, each participant told about their stories and skills, how they equipped the centers, how they solved the issue of duplication of assistance. During the group work, an interactive assessment of the preparation of the camp, for temporary and for long-term accommodation of IDPs was conducted. Arrangement and improvement of the territory: The life cycles of the camp were considered, what should be paid attention to for a decent life of IDPs at each stage of existence. Actualization of protection issues: Participants discussed what protection is and how to integrate it into camp activities. The 4 key components of protection integration were discussed. An interactive session was conducted for the participants to identify the roles and responsibilities of the actors involved in providing assistance in the camps. Roles and responsibilities: This block explained the essence of the roles of administration, coordination and management in camps and how they interact at different stages of the camp life cycle. A discussion was held among the participants on this topic and the types of protection they apply in their activities. Interactive on Security Audit on the example of selected ICPs. Issues of data protection and Code of Conduct among the relocated staff. Community participation: This block addressed the importance of involving IDPs in the life of the camp. The obstacles that affect inclusion were discussed, as well as different types of participation in community life. Stories about IDPs' relations with the community, educational elements. The conclusions were that there are not enough cultural and educational activities for these regions. Social and educational work. An interactive session was held with the participants on how to involve IDPs in participation. The participants shared their practical skills on this issue. Coordination and information management: In this block we looked at the importance of information gathering in collective centers and how it can affect the life of IDPs in the centers, and discussed different channels of information exchange. The methodologies used for data collection were described. We watched video materials on the topic "Communication". Monitoring of services: This block reviewed the process of service monitoring and its importance, described the link between SPHERE and service monitoring. The four protection principles according to the SPHERE Handbook and the technical aspects of humanitarian response covered by the minimum standards were reviewed. During the discussion, participants discussed how monitoring is implemented in practice in the collective centres where they operate. | Yes |  | Kirovohrad Oblast; | [27 empty] | ACTED | Kropyvnytskyi social dormitory | Local Government - Hromada;Non-Governmental Organization (NGO);Volunteers;Internal Displaced Persons;Local Government - Sectorial Department; |  |  | Kirovohrad Oblast - Kropyvnytskyi Raion;
22 | 2022-12-02 11:09 | 2022-12-02 11:29 | anonymous | [5 empty] | 2022-11-25 | 2022-11-25 | 1 | 16 | 12 | 4 | 0 | No |  |  |  | Russian;Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Rural;Peri-urban; | Introductory | Due to a complete power outage, the first day of the training (November 24) was cancelled. The program was reduced to a one-day training. During the day there were also 2 hours of work without light, with printed materials, interactives, but the lack of light hampered the work. In reducing the program, we minimally reduced the theory in all blocks and involved interactives and work in groups, with flip charts. The topics were in such an agendas: Introduction to the Course. Roles and Responsibilities. Introduction to Site Management. 3. Camp Life Cycle: Set-up, Site Improvement, Site Closure 4. Protection Mainstreaming 5. Coordination and information management Monitoring of the Center 6. 7. Community Participation Closing Message and Certificate giving Evaluation and wrap-up | Yes |  | Kirovohrad Oblast; | [27 empty] | ACTED | СС Znamenka hospital; СС School № 7 Znamenka -2; СС Adzham outpatient clinic; СС Social shelter and dormitory; Kropyvnytskyi local government; Sports club Borets; NGO House of Mercy | Internal Displaced Persons;Volunteers;Local Government - Sectorial Department; |  |  | Kirovohrad Oblast - Kropyvnytskyi Raion;
23 | 2022-12-05 09:57 | 2022-12-05 10:17 | anonymous | [5 empty] | 2022-11-29 | 2022-11-30 | 2 | 16 | 13 | 3 | 0 | No |  |  |  | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban; | Introductory | Introductory training on the management of collective centers for IDPs, all materials provided by the CCCM cluster | Yes |  | Kirovohrad Oblast; | [27 empty] | ACTED | Pedagogical University, Municipal Enterprise "Comfort", Bobrynytsia City Council, Kropyvnytskyi City Social Dormitory, representatives of the village council | Local Government - City Council;Local Government - Hromada; |  |  | Kirovohrad Oblast - Kropyvnytskyi Raion;
24 | 2022-12-05 10:19 | 2022-12-05 10:28 | anonymous | [5 empty] | 2022-12-01 | 2022-12-02 | 2 | 19 | 18 | 1 | 0 | No |  |  |  | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Peri-urban;Urban; | Introductory | Introductory training on the management of collective centers for IDPs, all materials provided by the CCCM cluster | Yes |  | Kirovohrad Oblast; | [27 empty] | ACTED | NGO "OGIC", College of Culture, Medical College, kindergartens, Charitable organization "Charitable Foundation "Oleksandria Assistance Center", Oleksandria City Council | Local Government - City Council;Non-Governmental Organization (NGO); |  |  | Kirovohrad Oblast - Oleksandriia Raion;
25 | 2022-12-07 16:49 | 2022-12-07 17:30 | anonymous | [5 empty] | 2022-12-06 | 2022-12-07 | 2 | 14 | 14 | 0 | 0 | No |  |  |  | Ukrainian; | CCCM Induction Training (for CCCM partners, SMS teams and Site Managers) | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Direct Application for benefit of IDPs and Host Community | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban; | Introductory | Course Introduction: Participants were introduced to the purpose of the course, gathered expectations for the training, and discussed the rules of the training; Introduction to CCCM: Participants were introduced to what camp management is, looked at different types of temporary housing and the stages of the camp life cycle. There was an interactive discussion that looked at how different IDPs need different protections and assistance. Roles and Responsibilities: This block explained the nature of the roles of administration, coordination and management in camps and how they interact at different stages of the camp life cycle. An interactive session was held for participants to identify the roles and responsibilities of participants involved in camp assistance. Landscaping and beautification: The life cycles of a camp were discussed, what should be taken into consideration for a dignified life of an IDP at each stage of the life cycle. During the discussion, each participant of the training shared their practical skills. During the group work, they created a roadmap of differences between temporary and long-term IDP centers. Discussed practical situations in each correctional center, who and how organized information exchange and reporting. Protection Accounting: we looked at a presentation on humanitarian principles and how they are put into practice in the form of the Code of Conduct and the Protection Audit. We interactively recorded the 4 key components of protection mainstreaming and conducted audit in groups by the example of 3 CC in Krivoy Rog (DUET, Industrial College and Polytechnic Professional College). Service monitoring: In this block the process of service monitoring and its importance were examined and the relationship between SPHERE and service monitoring was described. The four principles of protection under the SPHERE Guidelines and the technical aspects of humanitarian response covered by the minimum standards were discussed. During the discussion, participants were introduced to REACH monitoring data, all-Ukrainian and Dnepropetrovsk analytics. Discussed the goal and objectives of internal monitoring by their teams. Participation in community life: This block addressed the importance of IDP participation in the life of the collective center. Obstacles that affect involvement were discussed. An interaction was conducted to identify the need for participation for different categories of the population. The need for additional trainings on "Conflict management and stress management" was identified. The final block was built on the group work on the topic "What issues in the work with VPO require additional trainings, explanations, provisions or regulations". | Yes |  | Dnipropetrovsk Oblast; | [27 empty] | ACTED | DUET; Kfc DUET; Industrial College; Polytechnic Professional College; Krivoy Rog Gymnasium 46; Krivoy Rog Gymnasium 4; KZ "Center of social and psychological rehabilitation of children"; Krivoy Rog Gymnasium 27 | Volunteers;Internal Displaced Persons; |  |  | Dnipropetrovsk Oblast - Kryvyi Rih Raion;
26 | 2022-12-08 10:11 | 2022-12-08 10:21 | anonymous | [5 empty] | 2022-11-21 | 2022-11-26 | 5 | 27 | 17 | 7 | 0 | No |  |  |  | English;Ukrainian; | CCCM Training of Trainers | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Training of others who will then use theirs learning for direct benefit of IDPs | IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.); | Urban;Peri-urban; | Intermediary | Core CCCM package adapted by the CCCM Cluster in Ukraine with ongoing refinement spearheaded by the CapDev Working Group | No |  | Ivano-Frankivsk Oblast | [27 empty] | IOM | Prosvita, Zakarpattia Regional Charitable Organization “Edelweiss”, People in Need Slovakia, | UN Agency;Non-Governmental Organization (NGO);Local Government - Oblast; |  |  | Ivano-Frankivsk Oblast - Kolomyia Raion;Ivano-Frankivsk Oblast - Verkhovyna Raion;Ivano-Frankivsk Oblast - Ivano-Frankivsk Raion;Ivano-Frankivsk Oblast - Kalush Raion;Zakarpattia Oblast - Uzhhorod Raion;Zakarpattia Oblast - Tiachiv Raion;
27 | 2022-12-12 23:22 | 2022-12-12 23:34 | anonymous | [5 empty] | 2022-11-07 | 2022-11-11 | 5 | 20 | 10 | 10 | 0 | No |  |  |  | English;Ukrainian; | CCCM Training of Trainers | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Training of others who will then use theirs learning for direct benefit of IDPs | Transit Centers;IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.);Modular Houses sites;Out of IDP Collective and Modular Houses Sites; | Urban;Peri-urban; | Advanced | CCCM ToT based on contextualized package developed by CCCM CDWG for Ukraine. | Yes |  | Lviviska Oblast; | [27 empty] | CCCM Cluster | CCCM Cluster Ukraine, ACTED, NRC, Rokada, Neeka, Proliska, Right to Protection, 100% Life. | Non-Governmental Organization (NGO);International Non-Governmental Organization (INGO);UN Agency; |  |  | Ivano-Frankivsk Oblast - Ivano-Frankivsk Raion;Lviv Oblast - Lviv Raion;Rivne Oblast - Rivne Raion;Ternopil Oblast - Ternopil Raion;Vinnytsia Oblast - Vinnytsia Raion;Volyn Oblast - Volodymyr-Volynskyi Raion;Chernivtsi Oblast - Chernivtsi Raion;
28 | 2022-12-12 23:34 | 2022-12-12 23:43 | anonymous | [5 empty] | 2022-11-14 | 2022-11-18 | 5 | 22 | 17 | 5 | 0 | No |  |  |  | English;Ukrainian; | CCCM Training of Trainers | Sub-national - eg. for people who will work at the camp level or in one part of the country only (Oblast and Homadas) | Training of others who will then use theirs learning for direct benefit of IDPs | Transit Centers;IDP Collective Sites ( buildings that are being used as collective centers - educational facilities, health facilities, recreational facilities, hotels, etc.);Modular Houses sites;Out of IDP Collective and Modular Houses Sites; | Urban;Peri-urban;Rural; | Advanced | CCCM ToT standard and delivery of sessions based on CCCM package contextualized to Ukraine and revised by the CCCM CDWG. | Yes |  | Dnipropetrovsk Oblast; | [27 empty] | CCCM Cluster | CCCM Cluster Ukraine, UNHCR, ACTED, Tenth of April (TTA), Proliska, IOM, Alps Resilience, Right to Protection. | Non-Governmental Organization (NGO);UN Agency;International Non-Governmental Organization (INGO); |  |  | Dnipropetrovsk Oblast - Dnipro Raion;Kharkiv Oblast - Kharkiv Raion;Kirovohrad Oblast - Kropyvnytskyi Raion;Kyiv Oblast - Vyshhorod Raion;Odesa Oblast - Odesa Raion;Poltava Oblast - Poltava Raion;

## participants_gender
Data
Months | Total number of participants_ | female | male | gender not declared
Jun | 27 | 17 | 18 | 0
Jul | 58 | 36 | 22 | 0
Aug | 65 | 36 | 29 | 0
Sep | 109 | 78 | 31 | 0
Oct | 47 | 30 | 17 | 0
Nov | 154 | 104 | 47 | 0
Dec | 33 | 32 | 1 | 0
Total Result | 493 | 333 | 165 | 0

## Participants_Oblast
Duration of the event (in days) | - all -
Trainer(s) Name(s) | - all -
Oblast/Location of Event2 | Sum of Total number of participants
Chernivtsi Oblast | 7
Dnipropetrovsk Oblast; | 147
Ivano-Frankivsk Oblast | 54
Kirovohrad Oblast; | 83
National | 28
Odesa Oblast; | 25
Poltava Oblast | 22
Vinnytsia Oblast | 34
Zakarpattia Oblast | 60
(empty)
Lviviska Oblast; | 33
Total Result | 493
Timeline: Works in Excel 2013 or higher. Do not move or resize.