Date: 30th of October 2023

Venue: DRC Office - Aden

Chair: Ali Baowain – SN CCCM Cluster Coordinator, Aden AoR

Co-chair: Abdo Mohadeb – Head of Branches, Executive Unit

Participants: Attendance table below

**AGENDA**

* Introduction and welcoming
* Review of last meeting action points
* Protection Assistance, and Criteria [Mohammed Mukhawesh] [Manal Baaes Q&A]
* Community Contribution and Participation Project - Ateera IDP site Lahj
* Ex. Unit/ CCCM Cluster & Partners challenges and updates
* AoB

# Review of previous Action Points:

|  |  |  |
| --- | --- | --- |
| NO. م. | ACTION POINT النقاط المخرجة | Status  الحالة |
| 1 | Alshab sewage issue, Taybah Foundation implemented a sewage rehabilitationn in the site, but the issue still present. CCCM cluster to raise this to WaSH Cluster/ UNICEF. | Ongoing, sewage network rehabilitation is ongoing, Taybah is temporarily doing desludging for the flooded sewage. |
| 2 | CCCM Cluster will follow up with CCCM Governorate FP on the implementation of contingency planning specific for their governorate. | Ongoing;  Al Hodaidah, Taiz WC/ Taiz City, done  Aldhaleah, 30th of Nov  Aden, 31st of Dec  Shabowah, 30th of Nov  Hadramout, 30th of Nov  Lahj, 30th of Nov |
| 3 | NRC will meet with Omar Sumati and Sammir to discuss the intention survey results, and Abdo Mohadab will also talk to Omar Sumati about the proposed temporary relocation idea from his side. | IDPs refused the relocation to Attera2 or any other location out of Alanad. ExU identified a new land in Alanad, NRC HLP team is following up with ExU HLP FP on this regard |
| 4 | CCCM cluster will contact IMPACT Initiatives regarding the over validation process on sex and age disaggregated data section in the SMT. | Done, IMPACT Initiatives informed that they won’t be able to change at this specific time as it would affect the yearly trend analyses. However, there will be a review for the tool, where IMWG can address and do these modifications. |
| 5 | ACTED will share information about the IDPs who sold off site assets, and the ExU will follow up on this. | Ongoing, ACTED shared detailed information re the assets selling issue by 27th of Sept, ExU will share the investigation report with recommendation on the coming period. |
| 6 | FMF to share detailed information with ExU re the returnees who took the solar lamps from Al Kasarah IDP site. | Pending |
| 7 | ExU to decide on Arrounah IDP site location, either under Almmafer or Alwaziahiah district’s boundaries. ExU mentioned that this will require a decision from local authorities, which will need sometime on this. CCCM Cluster IM will locate the site location on the map and will use the OCHA boundaries mapping to decide. | As per OCHA maps, Arrunah is located in Al Maafer district, however there is no access from Al Maffer area, but Al Waziahiha district. |
| 8 | Liaise a meeting to discuss the way forward re Kadama Almaload assets. | Pending |
| 9 | AoBWC will share a report on its analysis of disabilities. ExU will share a report on disabilities that it conducted in four governorates. | Done |
| 10 | CCCM Cluster to invite Protection and Health Clusters to attend the October coordination meeting; CCCM Cluster will conduct a preparation session before the presentation. | Done |

# Protection Assistance, and Criteria [Mohammed Mukhawesh] [Manal Baaes Q&A]

*Protection Cluster Activity guide is attached.*



In addition to the standard Protection Cash Assistance (PCA), Protection was including also Multi-Purpose Cash Assistance (MPCA) program that had a broader scope than the PCA and could be used to cover a wider range of expenses, including healthcare. However, due to funding constraints, the MPCA program was discontinued last year.

Protection is supporting lifesaving cases that fall under other sectors. However, this is not their primary responsibility, and they intervene as a last resort.

Health partners support emergency healthcare but are also advocating for support for IDPs with chronic diseases. For some urgent cases, including surgical or chronic cases, Health cluster/partners is communicating directly with partners in health facilities or facility managers to serve such cases.

**AP: Health Cluster to share health service mapping with contacts of the focal point in health facilities and partners working in districts to facilitate referrals between CCCM and health actors.**

**AP: Protection Cluster to share their service mapping to be reached as a last resort in case a health partner is unable to respond to some health cases. Protection interventions will be based on protection criteria and a protection point of view**

**AP: CCCM and Health cluster to prepare for a joint mission into IDP sites in Aden, and Lahj.**

# Community Contribution and Participation Project - Ateera IDP site Lahj

*CCCM DRC Garabage Collection – Community participation and contribution project.*



Due to a lack of humanitarian interventions related to solid waste management, the situation in IDP sites deteriorated significantly. In response, DRC initiated a CLP to empower IDPs to take charge of solid waste management in their sites. this project was piloted in two sites, Ateera 1, and Alrebat IDP sites.

Prior to implementing this project, DRC conducted awareness sessions to educate IDPs about the importance of hygiene, waste disposal and highlight the potential for community-driven solutions. Through multiple FGDs, IDPs identified the challenges they faced in managing solid waste and proposed solutions. The ExU played a crucial role throughout the process, providing guidance and support from the awareness-raising phase to the facilitation and coordination/liaising with the Cleaning Fund.

A Community Committee was established with defined responsibilities, including ownership and maintenance of a small truck for garbage collection. To motivate IDPs and cover operational costs, the CC was tasked with collecting 500 Yemeni Rial from each IDP household. To ensure transparency, the CC was obligated to issue weekly financial reports detailing the use of the collected funds.

All agreed that such CLP has empowered IDPs to take ownership of solid waste management in their sites, leading to reducing the dependency on humanitarian assistances.

**AP: DRC to share BoQs and cost for the waste disposal CLP.**

# Ex. Unit/ CCCM Cluster & Partners challenges and updates

**New displacement & return:**

In November 2023, ExU reported that 168 HHs were displaced due to frontline clashes. Of these, 77 HHs fled to Marib governorate and 56 households fled to Al Hodaidah governorate. ExU also recorded the return of 19 HHs to Al Hodaidah. These households originated from Al Hodaidah, Abyan, Taiz, and Lahj.

**Floods:**

Cyclone Tej hit Yemen eastern governorates on 25th of October, it caused severe damage to people in these governorates, over 18,000 households are estimated to be affected, mainly in Al Maharah, followed by Hadramawt and Socotra governorates. Civilian homes and public infrastructure, including healthcare facilities and water networks, remain significantly damaged.

Cyclone affected 19 IDP sites in both governorates, Hadramout and Al Mahrah, and the establishment of temporarily collective centers. ExU reported the close of this temporarily established collective centers, some have moved to hotels, others staying with their relatives, the rest have returned to their houses that were partially damaged.

However, the pre-existing IDP sites were significantly damaged in Al Maharah and Hadramawt, affecting more than 400 HHs in detoritiated conditions, with limited humanitarian support.



ExU reported 12 eviction threat cases in Taiz, Hodeidah, Hadramout, Lahj and Aldhalea. ExU managed to sign and renew 7 land agreement in Al Hodaida, and 1 in Lahj.

OCHA will conduct Area Based Consultation for the 2024 Humanitarian response plan, CCCM cluster will nominate some CCCM ABACs to attend this consultations OCHA will share the invitation in due course of this month.

ExU is intending to monitor CCCM partners in the site

Schools in Al Buriqah are requesting 2000 Yemeni Rial from IDPs in order for there children study in the school. ExU to investigate if it is only against IDPs or also HC. Then to decide how to proceed

**AP: ExU to share the investigation results regarding incentives paid for Al Buriqah schools by IDPs.**

In Aldhalea, SI has a certain criterion for food/Cash assistance when applied on IDPs, they neglected all of IDPs. SI needs to coordinate with ACTED colleagues.

ExU needs to refer any NGOs who wants to intervene to ACTED, and vise versa. ExU Aden informed that they will insure the participation of ExU Aden FP in the ABAC meetings in Aden.

AoBWC managed sites mentioned that IDPs refused commonly livelihood projects, under CCCM CLP, and preferred the individual projects to ensure sustainalbility of these projects.

**AP: AoBWC to share FGDs and type of CLP projects with CCCM cluster to further discuss the issue in separate meetings.**

Host community water vendor charge each IDP HHs in Boaish site 2000 YER monthly. FMF, in collaboration with water corporation, is working to connect the site directly to the public network, reducing this expense for IDPs.

**AOB**

N/A

# SUMMARY OF ACTION POINTS

|  |  |  |
| --- | --- | --- |
| ITEM NO. | ACTION POINT | Responsible |
| 1 | Health Cluster to share health service mapping with contacts of the focal point in health facilities and partners working in districts to facilitate referrals between CCCM and health actors. | Health Cluster |
| 2 | Protection Cluster to share their service mapping to be reached as a last resort in case a health partner is unable to respond to some health cases. Protection interventions will be based on protection criteria and a protection point of view | Protection Cluster |
| 3 | CCCM and Health cluster to prepare for a joint mission into IDP sites in Aden, and Lahj. | CCCM/Health |
| 4 | DRC to share BoQs and cost for the waste disposal CLP. | DRC |
| 5 | AoBWC to share FGDs and type of CLP projects with CCCM cluster to further discuss the issue in separate meetings. |  |

# Attendance List

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No | Organization/Foundation Name | Participants Name | Participants Position | Participants Contact | Participants Email |
| 1 | ACTED | Maha Marta | CCCM Snr Office | 776800157 | maha.mohammed@acted.org |
| 2 | MSA | Seba Alasaggaf | Program Manager |  | sebaalsaggaf@msa-group.org |
| 3 | BCFHD | Ahmed Al-Shugaa | CCCM Coordinator |  |  |
| 4 | AOBWC | Bassam Abdulrahman | CCCM Coordinator | 770366692 | cccm.pm.aobwc@gmail.com |
| 5 | IOM | ZAID Buthaina | CCCM Officer |  | BZAID@iom.int |
| 6 | FMF | Nouras Al Haj | CCCM coordinator | 774930343 | nouras.alhaaj@fmfyemen.org |
| 7 | NRC | Fatima Fuad | CCCM Officer | 733656765 \770396403 | fatimah.fuad@nrc.no |
| 8 | NRC | Nasser Dabwan |  |  | nasser.dabwan@nrc.no |
| 9 | NRC | Amin Kaber |  |  | amin.jaber@nrc.no |
| 10 | DRC | Ammar Ahmed | CCCM TL |  | ammar.abdo@drc.ngo |
| 11 | DRC | Abeer Ahmed | Consortium Officer |  | abeer.thabet@drc.ngo |
| 12 | DRC | Ebrahim Mahmood Ahmed | CCCM IM |  | ebrahim.ahmed@drc.ngo |
| 13 | DRC | Shabbir Mortuja | PM |  | Shabbir.Mortuja@drc.ngo |
| 14 | GWQ | Mohammed Alaswdy |  | 774466653 | m.alaswdy@gwq-ye.org |
| 15 | NMO | Yasser Bin Shoib | Project Manager | 776161481 | yasser.bin.shuaib@nahdamakers.org |
| 16 | WaSH Cluster | Waheeb ultan | SN WaSH Cluster Coordinator |  |  |
| 17 | Muslim Hands | Duaa AlAhdel |  |  |  |
| 18 | IOL | Khaled Hassan | Representative |  |  |
| 19 | NRC | Ameen Gaber | CCCM Officer |  | amin.jaber@nrc.org |
| 20 | Consortium YDR | Abeer Thabet | CB Officer |  | abeer.thabet@drc.ngo |
| 21 | Abdulaziz | MAAKUM | Representative |  |  |
| 22 | SHS | Ibrahim Al Komim | CCCM Manager |  | cccm.manager@shsyemen.org |
| 23 | SHS | Nagi Ghareeb | CCCM Coordinator |  | Marib.coor@shsyemen.org |
| 24 | UNHCR | Osamah Albakili | CCCM Associate |  | alabkili@unhcr.org |
| 25 | Protection Cluster | Mohammed Mukhawesh | Protection Cluster |  | MUKHAWES@unhcr.org |
| 26 | Health Cluster | Manal Baaes | Health Cluster |  | baaeesm@who.int |
| 27 | EXU | Abdo Mohadab | Head of Branches | 734928109 | mhodab1@gmail.com |
| 28 | EXU | Mona | Assistant Head of Branches |  | Mona.alqamer@gmail.com |
| 29 | CCCM Cluster | Yasser Alshamiri | CCCM Cluster Marib |  | yalshameri@iom.int |
| 30 | CCCM Cluster | Mohammed Nasser | IM Associate |  | mubarak@unhcr.org |
| 31 | CCCM Cluster | Ali Baowain | Aden CCCM Cluster Coordinator | 739991270 | baowain@unhcr.org |